PROJECT PLAN

# TrustQuery AI — Engineering Project Plan

A forward-looking execution plan from prototype to pilot, with milestones, goals, and success criteria for the agentic NL2SQL platform.

# Vision & objective

Build a multi-agent system that lets business users ask questions about enterprise data in plain English and receive accurate, governed answers — without waiting on a data team, and without compromising on data security or human oversight where it matters. This plan covers the path from the current architecture and design (established in the accompanying PR/FAQ and architecture documents) to a validated pilot with a real business unit. The MVP prototype is deliberately scoped to a 2-week sprint that builds all four architecture layers end-to-end on sample data; hardening, production deployment decisions, and broader business-stakeholder integration are sequenced into the phases that follow it, not folded into the MVP itself.

## Guiding principles

- Open source and low-cost first: every component is free or self-hosted except the generation model itself, keeping the project cheap to run and easy to justify at each stage.

- Safety and governance are first-class, not bolted on: the HITL gate and PII masking ship in the same phase as core functionality, not as a later hardening pass.

- Iterate on real feedback: a real (or realistically masked) pilot with actual business users happens before any production hardening investment.

# Phased milestones

The MVP prototype is compressed to a 2-week sprint covering discovery and a full end-to-end build of all four architecture layers — not a partial slice. Hardening, production deployment options, and broader business-stakeholder integration are explicitly sequenced after it.

| Phase | Duration | Goals | Key deliverables | Success criteria |
| --- | --- | --- | --- | --- |
| Phase 0 — Discovery & MVP prototype | Weeks 1–2 | In a single 2-week sprint: finalize architecture decisions and stand up a working end-to-end prototype of all four layers on sample data | Turso schema + sample data (Layer 1); ChromaDB schema/exemplar index (Layer 2); Planner, Schema-Linking, SQL Generation, HITL Gate, Execution, and Response agents wired via LangGraph (Layer 3); DeepEval + self-hosted Langfuse + PII Governance agent wired for scoring and tracing (Layer 4); Chainlit UI for prototype demo only | End-to-end demo correctly answers ≥10–15 predefined questions against the Turso sample database, touching all four layers; HITL gate triggers in basic rule-based form on at least one seeded high-risk query; DeepEval scores are visible in Langfuse for every run |
| Phase 1 — Validation, governance & HITL hardening | Weeks 3–6 | Mature the prototype's validation and oversight layer beyond the 2-week baseline | HITL Gate thresholds tuned on real signal; PII Governance rules expanded and tested; golden dataset expanded to 100+ questions | DeepEval composite accuracy ≥85% on the golden set; 100% of tagged sensitive columns auto-masked in testing; HITL gate false-positive rate <5% on routine queries |
| Phase 2 — Pilot with real users | Weeks 7–10 | Validate with one real business unit on real or realistically masked data | Pilot rollout to one business unit; feedback loop instrumented; first DSPy/fine-tuning optimization cycle run and deployed via MLflow | Pilot user satisfaction ≥4/5; median end-to-end latency <10s (excluding HITL wait); HITL false-positive rate <10%; at least one optimization cycle completed and deployed |
| Phase 3 — Production hardening & scale | Weeks 11–16 | Prepare for general availability, including production deployment and UI | Multi-source connector support; cost monitoring dashboards; security/compliance review; runbooks & on-call documentation; UI refactored off the Chainlit prototype to a production chat interface (native Bedrock Agents chat UI, or a custom UI backed by API Gateway); directional evaluation of Amazon Bedrock AgentCore as a production hosting option for the agents (not committed in this plan) | Passes security/compliance review; cost per query within approved budget; runbooks accepted by platform operations; production UI live and no longer dependent on the prototype's Chainlit interface |

# Overall success metrics (north star)

- Query accuracy (DeepEval composite score): ≥90% at general availability

- Data-team ticket backlog reduction: 30–50% for onboarded domains

- HITL escalation rate: stabilizes below 15% of total queries

- Zero PII leakage incidents

- Median query latency: under 10 seconds for auto-approved queries

# Risks & mitigations

| Risk | Impact | Mitigation |
| --- | --- | --- |
| 2-week MVP timeline is tight for a full 4-layer scope | Prototype ships with rough edges or incomplete edge-case handling | Scope the prototype narrowly — one data domain, a small golden set, minimal UI polish — and explicitly defer performance/scale hardening to Phase 3 |
| Schema drift or stale metadata | Generated queries reference outdated or renamed columns | Automated nightly schema crawl (Layer 1) with change alerts feeding the schema-linking index |
| LLM cost overrun at scale | Per-query API cost grows faster than adoption | Deterministic GPT-4.1 mini at temperature 0, cached embeddings, per-query cost tracked in Langfuse with budget alerts |
| Hallucinated or incorrect SQL reaching users | Wrong answers erode trust | Self-healing execution loop, DeepEval regression gate in CI, and the HITL gate for high-risk queries |
| Reviewer fatigue / HITL bottleneck | Over-triggering slows down legitimate users | Tunable thresholds; escalation-rate monitoring feeds back into the Optimization agent |
| Data access delays from source system owners | Onboarding a domain stalls the timeline | Start data access conversations in Phase 0; pilot on a single domain first |
| Turso free-tier limits exceeded as pilot scales | Database usage caps are hit mid-pilot | Monitor usage against the 5GB/500M-read/10M-write cap; budget for the $4.99/month Developer tier as a low-cost upgrade path |
| Chainlit prototype UI is a dead end for production | Rework needed before broader rollout | Treat Chainlit as prototype-only from day one; UI refactor to a Bedrock-provided chat interface or a custom UI on API Gateway is scoped into Phase 3, not left as a surprise |

# Dependencies

- Data source and catalog access from source system owners

- Business SME time for golden dataset curation and review

- Security/compliance review bandwidth ahead of Phase 3

- Messaging/ticketing platform access (e.g., Slack or ServiceNow) for HITL reviewer routing

# Directional note: production deployment & UI

Two decisions are explicitly out of scope for this plan but worth flagging now so Phase 3 isn't a surprise. First, the UI: the Chainlit interface used for the MVP prototype is a development convenience, not a production plan — it will be refactored in Phase 3 to either the native chat interface provided within Amazon Bedrock Agents, or a custom UI backed by an API Gateway front end. Second, hosting: Amazon Bedrock AgentCore is a candidate option for running the agents in production, evaluated directionally as part of Phase 3 hardening. Neither decision needs to be made now — the architecture's agent and orchestration design (LangGraph-based, framework-agnostic at the hosting layer) doesn't lock in a specific production runtime, so this stays a Phase 3 decision informed by pilot learnings rather than a Phase 0 commitment.

# Team & ownership

Headcount and budget requirements to execute this plan are detailed separately in the companion Leadership Ask document, scoped to stakeholders and investors evaluating the resourcing decision.